## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Enter product and research details | MUST HAVE | None | Jahitha | Done
Sprint 1 | Sprint 1 | US-02 | Validate the entered research inputs | MUST HAVE | US-01 | Jahitha | Done
Sprint 1 | Sprint 1 | US-03 | Generate synthetic customer personas | MUST HAVE | US-02 | Jahitha | Done
Sprint 1 | Sprint 1 | US-04 | Add details to each customer persona | MUST HAVE | US-03 | Jahitha | Done
Sprint 1 | Sprint 1 | US-05 | Select the number of personas to generate | MUST HAVE | US-03 | Jahitha | Done
Sprint 1 | Sprint 1 | US-06 | Validate generated personas for relevance | SHOULD HAVE | US-05 | Jahitha | Done
Sprint 1 | Sprint 1 | US-07 | Display generated personas as cards | MUST HAVE | US-04 | Jahitha | Done
Sprint 2 | Sprint 2 | US-08 | Start an interview with a persona | MUST HAVE | US-07 | Jahitha | Done
Sprint 2 | Sprint 2 | US-09 | Remember previous persona interactions | MUST HAVE | US-08 | Jahitha | Done
Sprint 2 | Sprint 2 | US-10 | Ask the same question to multiple personas | MUST HAVE | US-03 | Jahitha | Done
Sprint 2 | Sprint 2 | US-11 | Display responses from different personas | SHOULD HAVE | US-10 | Jahitha | Done
Sprint 2 | Sprint 2 | US-12 | Generate responses based on persona behaviour | MUST HAVE | US-09 | Jahitha | Done
Sprint 2 | Sprint 2 | US-13 | Check responses for persona consistency | SHOULD HAVE | US-12 | Jahitha | Done
Sprint 2 | Sprint 2 | US-14 | Show customer adoption or purchase intent | SHOULD HAVE | US-09, US-12 | Jahitha | Done
Sprint 3 | Sprint 3 | US-15 | Compare responses from different personas | MUST HAVE | US-10, US-11 | Jahitha | Done
Sprint 3 | Sprint 3 | US-16 | Show loading and error messages | SHOULD HAVE | US-03, US-08 | Jahitha | Done
Sprint 3 | Sprint 3 | US-17 | Provide a complete research workspace | MUST HAVE | US-07, US-10 | Jahitha | Done
Sprint 3 | Sprint 3 | US-18 | Organize the FastAPI backend routes | MUST HAVE | US-02, US-08 | Jahitha | Done
Sprint 3 | Sprint 3 | US-19 | Connect the React frontend with FastAPI | MUST HAVE | US-18 | Jahitha | Done
Sprint 3 | Sprint 3 | US-20 | Provide project setup and documentation | SHOULD HAVE | US-18, US-19 | Jahitha | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7